## rebar2 -> rebar3
Level | Project | Curr. Rel. | Nxt Rel. | Source | Curr. Rel. | K2 Mod. | No. | Dep. Project | Dep. Rel. | Compilation | Eunit | CT | Cover | Dialyzer | Remarks
1 | https://github.com/K2InformaticsGmbH/dderl | 1.6.8 |  |  |  |  | 1 | https://github.com/K2InformaticsGmbH/erlpkg.git | raw | TBD
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 2 | https://github.com/K2InformaticsGmbH/imem.git | 1.6.0
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 3 | https://github.com/K2InformaticsGmbH/esaml | 8c278…
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 4 | https://github.com/K2InformaticsGmbH/cowlib.git | 1.0.0 [1.0.1]
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 5 | https://github.com/K2InformaticsGmbH/cowboy.git | 1.0.3
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 6 | https://github.com/K2InformaticsGmbH/mimetypes.git | 1.0
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 7 | https://github.com/K2InformaticsGmbH/erlimem.git | 1.2.7
1 | https://github.com/K2InformaticsGmbH/dderl | [5 empty] | 8 | https://github.com/K2InformaticsGmbH/erloci.git | 324eb…
2 | https://github.com/K2InformaticsGmbH/erlimem | 1.2.7 | [7 empty] | failed |  |  |  |  | compile: src/erlimem_session.erl:none: undefined parse transform 'lager_transform'
2 | https://github.com/K2InformaticsGmbH/erloci | 0.0.3pre-2 | [7 empty] | ok | failed | failed | 58% | warning: 104 | eunit: failed: 2. Skipped: 0. passed: 41
2 | https://github.com/K2InformaticsGmbH/erlpkg | n/a |  | https://github.com/c-bik/erlpkg | n/a | yes |  |  |  | n/a | n/a | n/a | n/a | n/a
2 | https://github.com/K2InformaticsGmbH/esaml | 1.1 |  | https://github.com/arekinath/esaml | 1.1 | yes | 1 | https://github.com/K2InformaticsGmbH/cowboy | 1.0.3 | ok | failed | prepared | 51% | warning: 3 | eunit: failed: 4. skipped: 0. passed: 37
2 | https://github.com/K2InformaticsGmbH/imem | 1.6.0 |  |  |  |  | 1 | https://github.com/K2InformaticsGmbH/erlscrypt.git | 1.1.7
2 | https://github.com/K2InformaticsGmbH/imem | [5 empty] | 2 | https://github.com/K2InformaticsGmbH/goldrush.git | 0.1.6
2 | https://github.com/K2InformaticsGmbH/imem | [5 empty] | 3 | https://github.com/K2InformaticsGmbH/jsx.git | 2.4.0 | [5 empty] | dependencies: why not version 2.6.2 ?
2 | https://github.com/K2InformaticsGmbH/imem | [5 empty] | 4 | https://github.com/K2InformaticsGmbH/lager.git | 2.1.0 | [5 empty] | dependencies: lager has version 2.1
2 | https://github.com/K2InformaticsGmbH/imem | [5 empty] | 5 | https://github.com/K2InformaticsGmbH/ranch.git | 1.1.0
2 | https://github.com/K2InformaticsGmbH/imem | [5 empty] | 6 | https://github.com/K2InformaticsGmbH/sext.git | b984b… | [5 empty] | dependencies: why not version 1.2 ?
2 | https://github.com/K2InformaticsGmbH/imem | [5 empty] | 7 | https://github.com/K2InformaticsGmbH/sqlparse.git | 1.5.4
2 | https://github.com/K2InformaticsGmbH/mimetypes.git | 1.0 |  | https://github.com/spawngrid/mimetypes | 1.0 | no
3 | https://github.com/K2InformaticsGmbH/cowboy | 1.0.3 |  | https://github.com/ninenines/cowboy | 1.1.2 | no | 1 | https://github.com/ninenines/cowlib | 1.3.0
3 | https://github.com/K2InformaticsGmbH/cowboy | [5 empty] | 2 | https://github.com/ninenines/ranch | 1.0.0
3 | https://github.com/K2InformaticsGmbH/erlscrypt | 1.1.7 |  | https://github.com/c-bik/erlscrypt | n/a | no |  |  |  | failed |  |  |  |  | compile: could not find d:\K2\erlscrypt_idea\erlscrypt\-f
3 | https://github.com/K2InformaticsGmbH/jsx | 2.6.2 |  | https://github.com/talentdeficit/jsx | 2.8.2 | no
3 | https://github.com/K2InformaticsGmbH/lager | 2.1 |  | https://github.com/erlang-lager/lager | 3.2.4 | yes | 1 | https://github.com/DeadZen/goldrush | 0.1.6 [0.1.9] | warning: 1 | failed | prepared | 70% | warning: 1 | compile: function i3l/1 is unused dependencies: why not K2 goldrush version ? eunit: faild: 17 skipped:0 passed: 169
3 | https://github.com/K2InformaticsGmbH/sext | 1.2 |  | https://github.com/uwiger/sext | 1.4.0 | yes | 1 | https://github.com/K2InformaticsGmbH/edown | 0.4 | warning: 1 | ok | prepared | 64% | warning: 1 | compile: function pp/1 unused dependencies: edown not properly versioned
3 | https://github.com/K2InformaticsGmbH/sqlparse | 1.5.4 |  |  |  |  | 1 | https://github.com/K2InformaticsGmbH/jpparse.git | 0.2.1 | ok | ok | prepared | 75% | warning: 2 | sqlparse_test.erl: change with file handling
4 | https://github.com/K2InformaticsGmbH/cowlib | 1.0.1 |  | https://github.com/ninenines/cowlib | 2.0.0-pre.1 | no
4 | https://github.com/K2InformaticsGmbH/edown | 0.4 |  | https://github.com/uwiger/edown | 0.8.1 | no
4 | https://github.com/K2InformaticsGmbH/goldrush | 0.1.6 |  | https://github.com/DeadZen/goldrush | 0.1.9 | no
4 | https://github.com/K2InformaticsGmbH/jpparse | 0.2.1 | [7 empty] | ok | ok | prepared | n/a | warning: 2 | jpparse.yrl: change with file handling
4 | https://github.com/K2InformaticsGmbH/ranch | 1.1.0 |  | https://github.com/ninenines/ranch | 1.3.2 | no

## Status
Level | Project | rebar2 | rebar3 | Compile | Scripts | Dialyzer | Xref | Eunit | CT | Cover | Jenkins | Cover final
1 | https://github.com/K2InformaticsGmbH/dderl | 1.68 | 1.8.0 | ok | 3/5 | error | > 100 | 1 ? | n/a | 2% | nok
2.1 | https://github.com/K2InformaticsGmbH/cowboy | 1.0.3 | see level 3.1
2.1 | https://github.com/K2InformaticsGmbH/cowlib | 1.3.0 | see level 3.1
2.1 | https://github.com/K2InformaticsGmbH/erlimem | 1.2.7 | 1.3.0 | n/a |  |  |  | nok |  | ?
2.1 | https://github.com/K2InformaticsGmbH/erloci | 324eb… | 0.1.0 | ok |  |  |  | 58 | ? | 61%
2.1 | https://github.com/K2InformaticsGmbH/erlpkg | raw | raw | n/a |  |  |  | n/a
2.1 | https://github.com/K2InformaticsGmbH/esaml | 8c278… | 2.1.0 | ok |  |  |  | 40 |  | 40%
2.1 | https://github.com/K2InformaticsGmbH/imem | 1.6.0 | 1.7.0 | now/0 | ok |  |  | 181 |  | 43%
2.1 | https://github.com/K2InformaticsGmbH/mimetypes | 1.0 | 1.0
3.1 | https://github.com/K2InformaticsGmbH/cowboy | 1.0.3 | 1.1.2
3.1 | https://github.com/K2InformaticsGmbH/cowlib | 1.3.0 | 1.0.2
3.1 | https://github.com/K2InformaticsGmbH/ranch | 1.1.0 | 1.3.2
3.2 | https://github.com/K2InformaticsGmbH/erlscrypt | 1.1.7 | 1.2.0 | Could Not Find ...\erlscrypt\-f |  |  |  | 9 |  | 52%
3.2 | https://github.com/K2InformaticsGmbH/goldrush | 0.1.6 | 0.1.9
3.2 | https://github.com/K2InformaticsGmbH/jsx | 2.6.2 | 2.8.2
3.2 | https://github.com/K2InformaticsGmbH/lager | 2.0.3 | 6daca… | i31/1 unused
3.2 | https://github.com/K2InformaticsGmbH/ranch | 1.1.0 | 1.3.2
3.2 | https://github.com/K2InformaticsGmbH/sext |  | 28152…
3.2 | https://github.com/K2InformaticsGmbH/sqlparse | 1.5.4 | 1.6.0 | shift/reduce |  |  |  | 397 |  | 75%
4 | https://github.com/K2InformaticsGmbH/edown |  | no longer needed
4 | https://github.com/K2InformaticsGmbH/jpparse | 0.2.1 | 0.3.0 | ok |  |  |  | 1 |  | 73%